## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Festive Dresses and Related Accessories For Different States of India. |  | 30 | 2021-08-15 | 2021-09-20 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-15 | 20-08--2021 | 5
1.2 | Finish webpage | 2021-08-21 | 2021-08-22 | 2
1.3 | Project Design | 2021-08-22 | 2021-08-26 | 5
2 | Coding
2.1 | Phase 1 | 2021-08-27 | 2021-09-03 | 7
2.2 | Phase 2 | 2021-09-04 | 2021-09-08 | 5
2.3 | Additional Features | 2021-09-09 | 2021-08-12 | 4
3 | Testing
3.1 | Phase 1 Testing | 2021-09-03 | 2021-09-04 | 2
3.2 | Modification /Any changes | 2021-09-05 | 2021-09-06 | 2
3.3 | Phase 2 Testing | 2021-09-11 | 2021-09-12 | 2
3.4 | Modification /Any changes | 2021-09-18 | 2021-09-19 | 2
3.5 | Final Testing | 2021-09-19 | 2021-09-20 | 2
4 | Documentation
4.1 | User Guide | 2021-09-19 | 2021-05-20 | 2
4.2 | Presentation | 2021-09-19 | 2021-05-20 | 2

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader
| Member Name | Akashy Salunkhe
| PRN No | 210543181089
| Description | Planning, Backend
2 | Role | Team Member
| Member Name | Supriya Birnale
| PRN No | 210543181109
| Description | Frontend,Connectivity
3 | Role | Team Member
| Member Name | Shubham Rote
| PRN No | 210543181089
| Description | Frontend,Connectivity
4 | Role | Team Member
| Member Name | Rahul Chavan
| PRN No | 210543181017
| Description | Database,Backend